A step-by-step model for setting up a children’s resilience programme

| Activity | Activity Content | Stakeholders | Output |
| --- | --- | --- | --- |
| Phase 0 Pre-planning |  |  |  |
| Assessment: Preliminary | Preliminary assessment | Community members /stakeholders and implementing organization | The preliminary assessment report will determine whether there is a need and necessary preconditions for the psychosocial intervention |
| SWOT analysis | Conduct SWOT analysis to explore opportunities for implementing a children’s resilience programme | Community members /stakeholders and implementing organization | Strengths, weaknesses, opportunities and threats for implementing a children’s resilience programme in the relevant community are identified |
| Memorandum of Understanding (MoU) | Begin to develop appropriate memoranda of understanding with ministry of education or other relevant ministry or governing body | Ministry or other governing body and implementing organization | Initial discussions of MoU are underway |
| Phase 1 Planning |  |  |  |
| Assessment: Detailed | Qualitative and quantitative data collection to explore challenges children are facing and opportunities for interventions | Community members /stakeholders (children, parents and caregivers, teachers, facilitators, others) and implementing organization | Detailed assessment report provides facts needed to guide the planning and implementation of the intervention |
| Target group identification | Identify possible school sites and/or out-of-school venues (e.g. CFS, youth clubs, orphanages etc.), appropriate groups of children with details on numbers and ages of children (within the range of 10 to 18 years old) | Within implementing organization, consult with relevant sectors, especially education and protection. Also consult with relevant MoE staff, headteachers, teachers, other facilitators. Also consult with other organizations/groups working with children in this area, e.g. cluster leads in protection and education. | Appropriate school sites and out-of-school venues are identified with numbers of children to be involved, and information on their age groups |
| Project design and budgeting | Design project based on assessment report and identified target groups. Develop budget based on resources available and needed activities | Implementing organization and stakeholders | Project design/document Budget |
| Hiring of national staff | Hiring of field coordinators and facilitator trainers if needed (in the beginning, trainers already employed by implementing organization can be used) | Human resources department of implementing organization | Hiring of XX number of field coordinators |
| Ensure availability of skilled and committed facilitators | Meetings and agreements with school management, teachers and/or other community groups and facilitators | Implementing organization and facilitators | Signed agreements |
| Indicator development/ baseline data | 2 days training of implementing organization’s field staff on developing indicators (e.g. wellbeing activity), data collection, analysis and report writing of baseline survey | Implementing organization, field staff, target group (beneficiaries – children, parents and caregivers, facilitators/teachers) | Indicators developed to be used for later monitoring and evaluation purposes. Baseline survey report with first measure of indicators, useful for determining which activities should be carried out with the children |
| Develop supervision and monitoring tools | Develop monitoring and supervision tools based on indicators and project design | Implementing organization, programme managers | Monitoring and supervision tools are developed and ready to use. |
| Adapt material e.g. workshops to specific context and culture | Make sure that the activities are culturally appropriate and aligned with baseline findings | Implementing organization, field staff | Finalized material for implementation |
| Translation of material | Translation of material to local language e.g. the finalized workshops | Implementing organisation, field staff | Finalized and translated material for implementation |
| Procurement of materials | Materials needed for all workshops are identified and procured | Administration of implementing organisation, programme manager and field coordinators | Materials needed are procured and available |
| Finalize MoU and any other needed agreements | Finalize Memorandum of Understanding between relevant groups; collect already existing agreements with schools/community groups and finalize any new agreements that have been drafted (e.g. clarify whether incentives will be provided) | Implementing organization, MoE, and other possibly relevant ministries, schools and/or out-of-school groups | Memorandum of understanding which includes psychosocial training and activities; clear agreements on facilitator’s roles and responsibilities, line management, role of field coordinators and links to referral systems |
| Identify or establish parent and caregiver committees | Identify existing or establish new parent and caregiver committees to serve as central points of communication between facilitators and parents and caregivers | Implementing organization, schools/community groups and parents and caregivers | Identification or establishing of new parents and caregivers committees to serve as central points of communication between facilitators and parents and caregivers |
| Orientation meetings in schools and/or communities | Hold XX number of 2-hour orientation meetings with relevant stakeholders. Obtain signed informed consent from parents and caregivers for children’s participation in workshops | Field staff/coordinators, teachers, facilitators, parents and caregivers, headteachers, volunteers, and any other adults who may be involved in ensuring the wellbeing of the children in the given community | Adults involved in the children’s lives and in the implementation of the psychosocial support programme are oriented on the programme. XX orientation meetings have been held. Informed consent forms obtained from parents and caregivers. |
| Confirm referral pathways and child protection systems | Identify appropriate referral pathways and systems and possible links/support to other child protection systems | Implementing organization and field coordinators | Referral pathways and systems are clear and easy to follow up on. Possible links to protection systems are included in programming. |
| Phase 2 |  |  |  |
| Develop detailed design of training programme for trainers | Identify training needs through consultations with relevant stakeholders | Implementing organization, relevant ministry representatives, sector managers in implementing organization, field coordinators, programme managers, other relevant partners | Finalize adapted training material according to the identified issues and capacity |
| Training of trainers | Carrying out XX training sessions for trainers | Implementing organization, relevant ministry representatives, sector managers in implementing organization, field coordinators, programme managers, other relevant partners | XX number of trained trainers |
| Develop detailed design of training programme for facilitators and field coordinators | Identify relevant training activities through use of the baseline survey, consultations with relevant stakeholders | Implementing organization, relevant ministry representatives, headteachers, teachers/facilitators, sector managers in implementing organization, field coordinators, programme managers, other relevant partners | Finalize adapted training materials according to the identified issues for selected sites |
| Training of facilitators and field coordinators | Carrying out XX training sessions for facilitators and field coordinators (this is done by master trainers) | Implementing organization, facilitators, field coordinators, other relevant participating stakeholders | XX number of trained facilitators and field coordinators |
| Hold workshops with children in schools and/or communities | Carry out pre-planned workshop activities with children in accordance with findings in the baseline survey | Children, parents and caregivers, facilitators, field coordinators, programme manager | XX number of children have participated in pre-planned workshops |
| Community activities | Activities that are identified and led by children | Community members and children | Community activities are carried out that help to improve the lives of the children and strengthen community wellbeing |
| Refresher training of facilitators | Refresher training of facilitators as needed | Implementing organization /facilitators | XX number of trained facilitators |
| Ongoing monitoring, supervision and support | Ongoing monitoring, supervision and support | Implementing organization, field coordinators, facilitators, children | Support is provided to field coordinators and facilitators. Monitoring reports are completed and stored securely. |
| Hold parents and caregiver meetings | Hold pre-planned meetings with parents and caregivers | Parents and caregivers, facilitators, field coordinators, programme managers | XX number of meetings with parents and caregivers are held |
| Hold parents and caregiver committee meetings | Hold parent and caregiver committee meetings at regular intervals (has to be coordinated with above so that no overlap occurs) | Parents and caregiver committee members | XX number of committee meetings held with parents and caregivers |
| Facilitate forums or meetings for facilitators to share their experience | Hold regular meetings with facilitators | Facilitators, field coordinators, programme managers | Regular meetings with facilitators |
| Initial exit strategy consideration | Initiate discussions and consideration of exit strategy | Implementing organization, relevant ministry representatives, headteachers, teachers/facilitators, sector managers in implementing organization, field coordinators, programme managers, other relevant partners | Initial planning of implementing organization’s exit from programme |
| Phase 3 |  |  |  |
| Mid-term evaluation | Conduct a mid-term evaluation about half way through planned implementation period to assess if intervention is achieving its goals. | Implementing organization, relevant ministry representatives, headteachers, teachers/facilitators, children, sector managers in implementing organization, field coordinators, programme managers, other relevant partners | Mid-term evaluation report including recommendations for adaptations or improvements to programme implementation |
| Final programme evaluation | Conduct a final evaluation at the end of the implementation period to assess if intervention succeeded in achieving its goals. | Implementing organization, relevant ministry representatives, headteachers, teachers/facilitators, children, sector managers in implementing organization, field coordinators, programme managers, other relevant partners | Final evaluation report including recommendations for future implementations of similar programmes |
| Exit programme | Gradually hand over programme to other stakeholders who may be in a position or interested to continue running it OR exit programme once it is completed | Implementing organization, relevant ministry representatives, headteachers, teachers/facilitators, children, sector managers in implementing organization, field coordinators, programme managers, other relevant partners | Programme ends or is continued but run by other stakeholders. |

Training in related areas can complement the impact of psychosocial programmes like this one and enhance the protective environment for children. Areas that are specially helpful include:

- disaster risk reduction

- accelerated learning programmes

- psychological first aid training.

- A children’s resilience programme should whenever possible be combined with other programmes and child protection systems.