Monitoring guidelines for field coordinators

1. General points on monitoring

What is monitoring?

Monitoring is the systematic and continuous collection, analysis and use of information for management control and decision-making (European Commission EuropeAid Co-operation Office, General Affairs. Project Cycle Management Training Courses Handbook, 2001).

Role of monitoring in project management

Programme managers have the challenging task of ensuring that projects stay on track and objectives are achieved. In real life it is very rare that a project goes exactly according to plan. Monitoring is a key process in navigating project management, providing accurate information to inform decision-making. Programme managers can identify and solve problems in the implementation of the project and assess progress in relation to what is planned.

Clear tasks and roles

Facilitators, field coordinators and programme managers are all involved in the monitoring process. Their roles, functions and responsibilities are different and should be clearly defined by the programme manager. When a report is needed, field coordinators and programme managers should be clear of its purpose and what information is required.

Purpose of monitoring

Systematic monitoring has a number of different purposes: programmes stay on track towards the achievements of its objectives children are offered the best possible programme facilitators are prepared and supported in the best possible way areas for additional training are identified resources are used in a cost-effective way.

Monitoring forms

Monitoring forms are usually developed to fulfil programme and donor requirements. Both facilitators and field coordinators must be trained in using the monitoring forms before embarking on the meetings with parents and caregivers and the workshops with the children. The forms are completed during or after each meeting or workshop, so as to report whilst the information is remembered clearly.

Processing and reporting data

Field coordinators collect and process data from the forms and summarize the findings in preparation for a monthly report. For monitoring to serve its purpose, the collected information needs to be communicated through the correct avenues at expected times. It is important to share the findings of the monitoring activities with all programme staff, to make sure everyone is aware of the progress and any issues that need to be dealt with.

2. Example of specific monitoring guidelines for field coordinators within a school setting

School visit

Be at the school 15 to 30 minutes before the beginning of each workshop. This time will be used to communicate with the headteacher, and facilitator(s). Be fully prepared for the workshop in order to support the facilitator with planning etc.

Headteacher visit

Visit the headteacher at least for 5 - 10 minutes and talk about the project. Ask questions like:

How are the workshops going?

What is the feedback from the facilitator, children, parents and caregivers?

Note the information given by the headteacher in the programme monitoring form.

Planning with facilitators

Plan to have between 15 – 30 minutes with the facilitator before the workshop starts. List all the planned activities for the workshop and discuss how the facilitator plans to run them. Ask the facilitator how you can help with the running of the activities.

Make an effort to establish a relationship of trust and support with the facilitator so that they feel free to consult with you on any issues that may arise. It may be difficult for a facilitator to be supervised and monitored, for example, if the field coordinator is younger than the facilitator. Some facilitators may interpret well-meant assistance from the field coordinators during the workshops as being corrected in front of the children. Agree before the workshop how to provide support during workshops.

School counsellor

If a school counsellor works at the school, make an effort to establish good relations with him/her and involve the counsellor in the children’s resilience programme. Visit the school counsellor when you are at the school and ask if and how he/she sees an impact on the children’s behaviour.

Referral system

Encourage close cooperation between the teacher/facilitator and the school counsellor.

Check if the school counsellor provides feedback on children who have been referred elsewhere for special services.

Encourage school counsellors to be involved in the meetings with parents and caregivers.

Encourage the involvement of parents and caregivers in the children’s resilience programme.

Monitoring of the workshops

Count the number of children present and agree with the facilitator that this is the number to be noted in the monitoring form.

Provide support during the running of the workshops, and help the facilitator as needed with activity implementation. Observe how the facilitator runs the activities and how the children participate and respond to the different activities.

If problems arise with the running of the workshop, help the facilitator deal with these, and follow up with a discussion with the facilitator when the workshop is over.

After the workshop discuss the following with the facilitator:

How do you feel the workshop went?

What went well?

What was difficult or challenging?

Did anything need special attention?  For example refer to something that was expressed, situations that were difficult to handle, activity instructions that were not clear, etc.

Complete the monitoring form immediately after the workshop to ensure their accuracy.