Preconditions for running a children’s resilience programme

The list of preconditions is not necessarily complete, and must be adapted to the local context.

Preconditions related to relevance

- Does the preliminary assessment indicate a need for a children’s resilience programme?

- Will a children’s resilience programme be culturally appropriate?

- Are children in the relevant age group available and interested in the programme?

- Are the suggested programme activities relevant to other activities in the community? Check they do not duplicate existing programmes.

Preconditions related to ownership

- Is there interest and commitment from the relevant authorities?

- Are parents and caregivers interested and committed to the programme?

- Are communities accepting and committed to this type of programme (including community leaders)?

Preconditions related to protection

- What local protection and psychosocial support mechanisms are in place? What are the referral pathways?

Preconditions related to implementation

- Are there schools/community centres or other venues available?

- Are the venues safe and secure?

- Do children have safe and secure access (for example, safe school roads)?

- Are children able to attend regularly? The programme works with children in groups, so the aim should be full attendance every time, due to group dynamics and the sequence of the activities.

- Is drinking water and are toilets available?

- Are the staff/volunteers available and committed for the whole programme period? (Remember that teachers and others in emergency situations are often overburdened with work and their own personal issues). The programme should not take important time and human resources from children’s education.

Note: If other organizations are implementing similar programmes, consider moving to another area or find a way of working together to supplement their work.